## Sheet1
Construction Lessons Learned Log
Company Name
Project Name:
Project #
Date Completed:
| DESCRIPTION | WIN / LOST | IMPACT ON CURRENT PROEJCT? | CHANGES FOR FUTURE PROJECTS | ACTION ITEMS | ADDITIONAL COMMENTS
1 | Schedule went off track and we didn’t get around to updating it. | LOST | We weren't able to identify when schedule slippages occurred properly. Changes couldn’t be managed | Track the schedules more closely Ensure regular updates | Prepare a procedure for updating the schedule on a consistent basis to ensure consistency across the organization.
2 |  | WIN
3 |  | LOST
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24