## REMARKS
REMARKS ON THE PROJECT EXECUTIVE SUMMARY
When using this Project Executive Summary file, kindly note that:
1) One file is applicable for every on going project. It shall be updated and submitted on a monthly basis by the respective project managers.
2) Project managers only needs to work on the INPUT tab. Actually, it would be appreciated if you do not edit any date/value on the OUTPUT tab, which has been adapted to automatically process the INPUT data and show them by charts.
3) Once this file is updated, each project responsible shall email it (both Excel and pdf formats) to the CEO and the Projects Director, by latest one working day before the monthly Project Review Meeting.
4) The goal of this meeting format is to focus on the main project management items, highlight the project issues and the remedy actions, simplify the preparation and to empower every project team member.
5) On the INPUT tab, kindly edit only the dates/values in green cells. The others are auxiliary calculation cells and, if they are modified, the charts on the OUTPUT tab will not be correct.
6) On the INPUT tab you shall update dates/values with respect to two points in time (current and at completion of the project) and two criteria (actual and forecasted). The combination of the two points in time and the two criteria gives us four cases to be analysed, according to the table below:
| ANALYSIS CASES (FORMAL) |  | POINT IN TIME
|  |  | CURRENT (TO DATE) | AT COMPLETION
| CRITERIA | FORECASTED (PROGRAMMED) | Forecasted Current | Forecasted at Completion
|  | ACTUAL (REAL) | Actual Current | Realistic at Completion
7) The aforementined four cases can be translated into common nomenclature as shown in the table below:
| ANALYSIS CASES (COMMON) |  | POINT IN TIME
|  |  | CURRENT (TO DATE) | AT COMPLETION
| CRITERIA | FORECASTED (PROGRAMMED) | Where we planned to be now | Where we planned to be at completion
|  | ACTUAL (REAL) | Where we are now | Where we will be at completion (if nothing changes)
8) Anyway, these four cases are applied in this file to the Programme of Works, the Revenues, the Costs and the Gross Profit of the project, always referred to cumulative values.
9) During the Projects Review Meetings, each Project Manager shall explain the four charts on the OUTPUT tab, having only 1 minute per chart to do so. It should be enough time to highlight the major deviations (if any) between the actual and the forecasted criteria.
10) After that, the project team (formed by the Project Manager, the Quantity Surveyor, the Site Agent and any other person invited to the meeting, according to the matters to discuss) will have additional time to explain the Claims records, warn the Projects Director about any Contractual Matter that may cause future issues and provide further Comments on the overall presentation.
11) The maximum total time for each project review shall be 60 minutes.

## INPUT
|  | MAIN DATA FOR THE PROJECT EXECUTIVE SUMMARY |  |  |  |  | DO NOT MODIFY ANY CELL ON THESE TWO COLUMNS, PLEASE!!!
EDIT ONLY THE CELLS IN YELLOW
Project and Summary Identification: | [6 empty] | Their values/dates are used on calculations
| Project Code: |  |  | xxxxxx
| Project Brief Name: |  |  | the project
| Reporting Date of this Executive Summary (end of): |  |  | 2016-03-30 | (Month) |  | 2016-03-30 |  | Programme of Works | Where we planned to be now.
Updated Programme of Works (PoW):
| Commencement Date of the Project: |  |  | 2015-01-12 |  |  | 2015-01-12
| Originally Approved Date for Completion: |  |  | 2016-01-12
| Currently Approved Extension of Time for Completion: |  |  | 64 | cumulative days
| Currently Approved Date for Completion: |  |  | 2016-03-16 |  |  | 2016-03-16 |  |  | Where we planned to be at completion
| Current Delay (-) or Advancement (+) with respect to Currently Approved PoW: |  |  | -120 | days
| Actual Date on the PoW (modified by Current Delay/Advancement): |  |  | 2015-12-01 |  |  | 2015-12-01 |  |  | Where we are now.
| Realistic Date for Completion: |  |  | 2016-07-29 |  |  | 2016-08-01 |  |  | Where we will be at completion (if nothing changes).
Actual Current Revenue (taken from the Latest Payment Certificate/Invoice Approved by the Engineer/Employer):
| Date of Issue of the Latest Payment Certificate: |  |  | 2016-05-03
| No. of the Latest Payment Certificate: |  |  | 14
| For the Works Done Until End of: |  |  | 2016-02-29 | (Month)
| Current Cumulative Certified Value of Works Executed: |  |  | 94264456 | until end of | 2016-02-29
| Current Cumulative Certified Discount, VAT exc.: |  |  | -2827933.7 | until end of | 2016-02-29
| Current Cumulative Certified Variations of Prices, VAT exc. : |  |  | 0 | until end of | 2016-02-29
| Current Cumulative Certified Variations of Works, VAT exc. : |  |  | 0 | until end of | 2016-02-29
| Current Cumulative Certified Company's Claims, VAT exc. : |  |  | 0 | until end of | 2016-02-29 | 0 | Million Rs
| Current Cumulative Certified Employer's Claims, VAT exc. : |  |  | 0 | until end of | 2016-02-29 | 0 | Million Rs
| Current Cumulative Certified Credit for Materials, VAT exc.: |  |  | 0 | until end of | 2016-02-29
| Current Cumulative Certified Debit for Materials, VAT exc.: |  |  | 0 | until end of | 2016-02-29
| Current Cumulative Certified Bankable Revenue: |  |  | 91436522.3 | until end of | 2016-02-29 | 91.4365 | Million Rs | Bankable Revenue | Where we are now.
| Current Cumulative Certified Total Amount, VAT exc. : |  |  | 76459080.55 | until end of | 2016-02-29
| Current Cumulative Certified Total Amount, VAT inc. : |  |  | 87927942.6325 | until end of | 2016-02-29
Forecasted Current Revenue:
| Current Cumulative Forecasted Value of Works Executed: |  |  | 95864583 | until end of | 2016-02-29
| Current Cumulative Forecasted Bankable Revenue: |  |  | 93036649.3 | until end of | 2016-02-29 | 93.0366 | Million Rs |  | Where we planned to be now.
Forecasted Revenue at Completion:
| Originally Awarded Contract Price, VAT exc.: |  |  | 186954585.66 | until end of | 2016-07-29 | 186.9546 | Million Rs |  | Where we planned to be at completion
| Originally Awarded Contract Price, VAT inc.: |  |  | 214997773.509 | until end of | 2016-07-29
| Forecasted Value of Works Executed at Completion: |  |  | 151404320.67 | until end of | 2016-07-29
| Forecasted Discount at Completion, VAT exc.: |  |  | -4542129.6201 | until end of | 2016-07-29
| Forecasted Variations of Prices at Completion, VAT exc.: |  |  | 0 | until end of | 2016-07-29
| Forecasted Variations of Works at Completion, VAT exc.: |  |  | 7189274 | until end of | 2016-07-29
| Forecasted Sotravic's Claims at Completion, VAT exc.: |  |  | 13500000 | until end of | 2016-07-29 | 13.5 | Million Rs
| Forecasted Employer's Claims at Completion, VAT exc.: |  |  | -4178533 | until end of | 2016-07-29 | -4.1785 | Million Rs
| Forecasted Credit for Materials at Completion, VAT exc.: |  |  | 0 | until end of | 2016-07-29
| Forecasted Debit for Materials at Completion, VAT exc.: |  |  | 0 | until end of | 2016-07-29
| Forecasted Bankable Revenue at Completion: |  |  | 163372932.0499 | until end of | 2016-07-29
| Forecasted Outstanding Retention to be Released after Completion, VAT exc.: |  |  | 9347729.28 | until end of | 2016-07-29
| Revised Contract Price, VAT exc.: |  |  | 172720661.3299 | until end of | 2016-07-29 | 172.7207 | Million Rs |  | Where we will be at completion (if nothing changes).
| Revised Contract Price, VAT inc.: |  |  | 198628760.5294 | until end of | 2016-07-29
Current Allowables and Costs, until end of the reporting date: |  |  |  | 2016-03-30
| Current Cumulative Project Allowables, VAT exc. : |  |  | 98579098.46 | until end of | 2016-03-30 | 98.5791 | Million Rs | Cost | Where we planned to be now.
| Current Cumulative Project Cost posted on BuildSmart, VAT exc. : |  |  | 128833145.6 | until end of | 2016-03-30 |  |  |  | 2016-03-30
| Adjustment of the Current Cumul. Project Cost posted on ERP, VAT exc. : |  |  | 318455 | until end of | 2016-03-30
| Adjusted Current Cumulative Project Cost, VAT exc. : |  |  | 129151600.6 | until end of | 2016-03-30 | 129.1516 | Million Rs |  | Where we are now.
Allowables and Costs until the date considered on the Latest Payment Certificate/Invoice: |  |  |  |  | 2016-02-29
| Current Cumulative Project Allowables, VAT exc. : |  |  | 96000000 | until end of | 2016-02-29 | 96 | Million Rs |  | Where we planned to be now.
| Current Cumulative Project Cost posted on BuildSmart, VAT exc. : |  |  | 125000000 | until end of | 2016-02-29 |  |  |  | 2016-02-29
| Adjustment of the Current Cumul. Project Cost posted on ERP, VAT exc. : |  |  | 300000 | until end of | 2016-02-29
| Adjusted Current Cumulative Project Cost, VAT exc. : |  |  | 125300000 | until end of | 2016-02-29 | 125.3 | Million Rs |  | Where we are now.
Forecasted Allowables and Costs at Completion:
| Forecasted Project Allowables at Completion, VAT exc. : |  |  | 150829644 | until end of | 2016-07-29 | 150.8296 | Million Rs |  | Where we planned to be at completion
| Realistic Project Cost at Completion, VAT exc. : |  |  | 187309817.46 | until end of | 2016-07-29 | 187.3098 | Million Rs |  | Where we will be at completion (if nothing changes).
Actual Gross Loss/Profit, when taking the COSTS until the reporting date: |  |  |  | 2016-03-30
| Current Cumulative Forecasted Gross Loss (-) / Profit (+): |  |  | -5542449.16 | until end of | 2016-03-30 | -5.5424 | Million Rs | Loss/Profit | Where we planned to be now.
| Current Cumulative Actual Gross Loss (-) / Profit (+): |  |  | -37715078.3 | until end of | 2016-03-30 | -37.7151 | Million Rs |  | Where we are now. | 2016-03-30
Actual Gross Loss/Profit, when taking the COSTS until the date considered on the Latest Payment Certificate/Invoice: | [5 empty] | 2016-02-29
| Current Cumulative Forecasted Gross Loss (-) / Profit (+): |  |  | -2963350.7 | until end of | 2016-02-29 | -2.9634 | Million Rs |  | Where we planned to be now.
| Current Cumulative Actual Gross Loss (-) / Profit (+): |  |  | -33863477.7 | until end of | 2016-02-29 | -33.8635 | Million Rs |  | Where we are now. | 2016-02-29
Gross Loss/Profit at Completion:
| Forecasted Gross Loss (-) / Profit (+) at Completion: |  |  | 36124941.66 | until end of | 2016-07-29 | 36.1249 | Million Rs |  | Where we planned to be at completion
| Realistic Gross Loss (-) / Profit (+) at Completion: |  |  | -14589156.1301 | until end of | 2016-07-29 | -14.5892 | Million Rs |  | Where we will be at completion (if nothing changes).
Current Potential Company Claims:
| Payments on Claims to be Notified or Substantiated (not Certified yet) |  |  | 7189273.98 | until end of | 2016-03-30
| Current Potential Claims (Certified + to be Notified/Substantiated) |  |  | 7189273.98 | until end of | 2016-03-30 | 7.1893 | Million Rs
Current Potential Employer's Claims:
| Payments on Employer's Claims to be Notified or Substantiated (not Certified yet) |  |  | -4178533 | until end of | 2016-03-30
| Current Potential Employer's Claims (Certified + to be Notified/Substantiated) |  |  | -4178533 | until end of | 2016-03-30 | -4.1785 | Million Rs
OTHER CONTRACTUAL MATTERS (describe them briefly in the 10 rows below)
1
2
3
4
5
6
7
8
9
10
COMMENTS (type further information in the 12 rows below)
1 | PROGRAMME OF WORKS
2
3 | BANKABLE REVENUES
4
5 | COSTS
6
7 | GROSS LOSS/PROFIT
8
9 | CLAIMS
10
11 | CONTRACTUAL MATTERS
12
Company
Employer
Note on B14: This is the date that shall be considered in our current PoW and FORECASTS. If not, kindly update them accordingly before continuing with this Executive Summary...
Note on G16: This value shall be typed as: * NEGATIVE if the actual execution is DELAYED with respect to the approved PoW. * POSITIVE if the actual execution is ADVANCED with respect to the approved PoW.
Note on B18: Considering, from a REALISTIC point of view, if the current and other potential future DELAYS can be REDUCED/AMENDED (or NOT), to comply with the currently Approved Date for Completion.
Note on B20: Latest Payment Certificate approved by the Engineer/Employer (or latest INVOICE submitted by Sotravic, if the Contract does not require Payment Certificates)
Note on B24: It ONLY concerns the BILLS of the BoQ. Therefore, it EXCLUDES any other AMENDMENT of REVENUE, CONTRACTUAL or NOT, CERTIFIED or NOT, POTENTIAL or NOT, such as: * Discounts (because of Sotravic's Tender) * Variations of Prices * Variations of Works * Sotravic's or Employer's Claims * Advance Payment (Received or Reimbursed) * Retention (Hold or Released) * VAT, TDS and other taxes.
Note on B26: Discount included in Sotravic's Tender, usually considered as a % of the Contract Price
Note on G26: This value shall always be NEGATIVE or NIL!!!
Note on B27: Only the CERTIFIED Variations
Note on B28: Only the CERTIFIED Variations
Note on B29: Only the CERTIFIED Claims
Note on G29: This value shall always be POSITIVE or NIL!!!
Note on B30: Only the CERTIFIED Claims
Note on G30: This value shall always be NEGATIVE or NIL!!!
Note on G31: This value shall always be POSITIVE or NIL!!!
Note on G32: This value shall always be NEGATIVE or NIL!!!
Note on B34: The Bankable Revenue INCLUDES the CERTIFIED: * Value of Works Executed (BoQ bills) * Discount (because of Sotravic's Tender) * Variations of Prices * Variations of Works * Sotravic's and Employer's Claims * Credit/Debit for Materials Note that it EXCLUDES: * Advance Payment (Received and Reimbursed) * Retention (Hold and Released) * VAT, TDS and other taxes
Note on B39: It ONLY concerns the BILLS of the BoQ. Therefore, it EXCLUDES any other AMENDMENT of REVENUE, CONTRACTUAL or NOT, CERTIFIED or NOT, POTENTIAL or NOT, such as: * Discounts (because of Sotravic's Tender) * Variations of Prices * Variations of Works * Sotravic's or Employer's Claims * Advance Payment (Received or Reimbursed) * Retention (Hold or Released) * VAT, TDS and other taxes.
Note on B41: The Bankable Revenue INCLUDES the CERTIFIED: * Value of Works Executed (BoQ bills) * Discount (because of Sotravic's Tender) * Variations of Prices * Variations of Works * Sotravic's and Employer's Claims * Credit/Debit for Materials Note that it EXCLUDES: * Advance Payment (Received and Reimbursed) * Retention (Hold and Released) * VAT, TDS and other taxes
Note on B46: It ONLY concerns the BILLS of the BoQ. Therefore, it EXCLUDES any other AMENDMENT of REVENUE, CONTRACTUAL or NOT, CERTIFIED or NOT, POTENTIAL or NOT, such as: * Discounts (because of Sotravic's Tender) * Variations of Prices * Variations of Works * Sotravic's or Employer's Claims * Advance Payment (Received or Reimbursed) * Retention (Hold or Released) * VAT, TDS and other taxes.
Note on B48: Discount included in Sotravic's Tender, usually considered as a % of the Contract Price
Note on G48: This value shall always be NEGATIVE or NIL!!!
Note on B49: Only the CERTIFIED Variations and those the Engineer/Employer WILL LIKELY ACCEPT
Note on B50: Only the CERTIFIED Variations and those the Engineer/Employer WILL LIKELY INSTRUCT
Note on B51: Only the CERTIFIED Claims and those the Engineer/Employer WILL LIKELY ACCEPT
Note on B52: Adding the ALREADY CERTIFIED EMPLOYER'S CLAIMS + those the Employer WILL LIKELY PROCESS in the future, such as the DAMAGE RISK for not complying with the DATE FOR COMPLETION (if that's the case).
Note on G52: This value shall always be NEGATIVE or NIL!!!
Note on G53: This value shall always be POSITIVE or NIL!!!
Note on G54: This value shall always be NEGATIVE or NIL!!!
Note on B56: The Bankable Revenue INCLUDES the FORECASTED: * Value of Works Executed (BoQ bills) * Discount (because of Sotravic's Tender) * Variations of Prices * Variations of Works * Sotravic's and Employer's Claims * Credit/Debit for Materials Note that it EXCLUDES: * Advance Payment (Received and Reimbursed) * Retention (Hold and Released) * VAT, TDS and other taxes
Note on G58: POSITIVE or NIL
Note on B60: Including the Outstanding Retention to be Released after Completion
Note on G65: This value is the total SUM of: * BuidSmart Missing Costs: those already incurred in our project but not posted yet. They shall be considered as POSITIVE. * BuidSmart Wrong Costs: those wrongly posted (not incurred yet or incorrectly allocated to our project). They shall be considered as NEGATIVE.
Note on G70: This value is the total SUM of: * BuidSmart Missing Costs: those already incurred in our project but not posted yet. They shall be considered as POSITIVE. * BuidSmart Wrong Costs: those wrongly posted (not incurred yet or incorrectly allocated to our project). They shall be considered as NEGATIVE.
Note on G86: POSITIVE OR NIL!!!
Note on G89: NEGATIVE OR NIL!!!

## OUTPUT
[9 empty] | PROJECT EXECUTIVE SUMMARY | [30 empty] | Project Code: | xxxxxx | [13 empty] | Reporting Date (end of): | 2016-03-30
[40 empty] | Project Name: | the project
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | Where we planned to be now.
[5 empty] | 1: LEGEND; 10: Completed to date (Forecasted Date/Value); 29: Outstanding (Not Completed yet); the project 46: ▼; the project 47: Completion Limit (Forecast Criterion) |  |  | Where we planned to be at completion.
[5 empty] | 10: Completed to date (Actual Date/Value); 29: Not Applicable (Beyond Completion Limits); the project 46: ▲; the project 47: Completion Limit (Actual Criterion) |  | Where we are now. | Where we will be at completion (if nothing changes).
| 1 - PROGRAMME OF WORKS | [71 empty] | 18.9 | = project duration (months)
|  |  | (Month) | [69 empty] | 9 | = scale adjustment |  | 31 | 2015-01-12 | time axis 2015-01-12 to 2016-09-06
|  |  |  | Current Approved Date for Completion: | 2016-03-19: 2016-03-16
F | Reporting Date (end of) | [71 empty] | ▼ | to date value | limit at completion | bar: 2016-03-19
|  |  | 2016-03-30 | [69 empty] | v | 2016-03-30 | 2016-03-16 | . | bar: 2015-01-12 to 2016-09-06
| Actual Date on the PoW (modified by Current Delay/Advmt.) |  | 2015-12-01 | [69 empty] | a | 2015-12-01 | 2016-08-01 | . | bar: 2015-01-12 to 2015-12-02; 2016-08-10 to 2016-09-06
A | [72 empty] | ▲ | bar: 2016-08-01
|  |  |  | Realistic Date for Completion: | 2016-07-05: 2016-08-01
| 2 - BANKABLE REVENUE according to the latest Payment Certificate/Invoice, for the works executed until end of |  |  |  | 2015-08-16: 2016-02-29
|  |  | (Million Rs) |  | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 3 | = scale adjustment
|  |  |  | Original Contract Price, VAT exc.: | 2016-02-29 183: 186.9546
F | Current Cumulative Forecasted Bankable Revenue | [71 empty] | ▼ | today's value | limit at completion | bar: 2016-02-29 186
|  |  | 93.0366 | [69 empty] | v | 93.0366 | 186.9546 | . | bar: 3 to 2016-02-29 93; 2016-02-29 189 to 2016-02-29 204
| Current Cumul. Actual (CERTIFIED) Bankable Reve. |  | 91.4365 | [69 empty] | a | 91.4365 | 172.7207 | . | bar: 3 to 2016-02-29 90; 2016-02-29 177 to 2016-02-29 204
A | [72 empty] | ▲ | bar: 2016-02-29 174
|  |  |  | Revised Contract Price, VAT exc.: | 2016-02-29 171: 172.7207
| 3A - COSTS until end of | 2016-03-30 |  | (the Reporting Date)
|  |  | (Million Rs) |  | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 3 | = scale adjustment
|  |  |  | Forecasted Allowables at Comp., VAT exc.: | 147: 150.8296
F | Current Cumulative Allowables | [71 empty] | ▼ | today's value | limit at completion | bar: 150
|  |  | 98.5791 | [69 empty] | v | 98.5791 | 150.8296 | . | bar: 3 to 99; 153 to 204
| Current Cumulative Adjusted Costs |  | 129.1516 | [69 empty] | a | 129.1516 | 187.3098 | . | bar: 3 to 129; 189 to 204
A | [72 empty] | ▲ | bar: 186
|  |  |  | Realistic Costs at Completion, VAT exc.: | 183: 187.3098
| 3B - COSTS until end of | 2016-02-29 |  | (the Date considered on the Latest Payment Certificate/Invoice):
|  |  | (Million Rs) |  | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 99 | 102 | 105 | 108 | 111 | 114 | 117 | 120 | 123 | 126 | 129 | 132 | 135 | 138 | 141 | 144 | 147 | 150 | 153 | 156 | 159 | 162 | 165 | 168 | 171 | 174 | 177 | 180 | 183 | 186 | 189 | 192 | 195 | 198 | 201 | 204 | 3 | = scale adjustment
|  |  |  | Forecasted Allowables at Comp., VAT exc.: | 147: 150.8296
F | Current Cumulative Allowables | [71 empty] | ▼ | today's value | limit at completion | bar: 150
|  |  | 96 | [69 empty] | v | 96 | 150.8296 | . | bar: 3 to 96; 153 to 204
| Current Cumulative Adjusted Costs |  | 125.3 | [69 empty] | a | 125.3 | 187.3098 | . | bar: 3 to 126; 189 to 204
A | [72 empty] | ▲ | bar: 186
|  |  |  | Realistic Costs at Completion, VAT exc.: | 183: 187.3098
| 4A - GROSS LOSS (-) / PROFIT (+) , when taking the COSTS until end of |  |  |  | 33: 2016-03-30; 90: LOSS ←; 93: → PROFIT
|  |  | (Million Rs) |  | -40.31 | -38.92 | -37.53 | -36.14 | -34.75 | -33.36 | -31.97 | -30.58 | -29.19 | -27.8 | -26.41 | -25.02 | -23.63 | -22.24 | -20.85 | -19.46 | -18.07 | -16.68 | -15.29 | -13.9 | -12.51 | -11.12 | -9.73 | -8.34 | -6.95 | -5.56 | -4.17 | -2.78 | -1.39 | -1e-07 | 1.39 | 2.78 | 4.17 | 5.56 | 6.95 | 8.34 | 9.73 | 11.12 | 12.51 | 13.9 | 15.29 | 16.68 | 18.07 | 19.46 | 20.85 | 22.24 | 23.63 | 25.02 | 26.41 | 27.8 | 29.19 | 30.58 | 31.97 | 33.36 | 34.75 | 36.14 | 37.53 | 38.92 | 40.31 | 41.7 | 43.09 | 44.48 | 45.87 | 47.26 | 48.65 | 50.04 | 51.43 | 52.82 | 1.39 | = scale adjustment
|  |  |  | Forecasted Gross Loss/Profit at Completion: | 159: 36.1249
F | Current Cumulative Forecasted Gross Loss (-) / Profit (+) | [71 empty] | ▼ | today's value | limit at completion | bar: 168
|  |  | -5.5424 | [69 empty] | v | -5.5424 | 36.1249 | . | bar: 81 to 204
| Current Cumulative ACTUAL Gross Loss (-) / Profit (+) |  | -37.7151 | [69 empty] | a | -37.7151 | -14.5892 | . | bar: 3 to 204
A | [72 empty] | ▲ | bar: 60
|  |  |  | Realistic Gross Loss/Profit at Completion: | 51: -14.5892
| 4B - GROSS LOSS (-) / PROFIT (+) , when taking the COSTS until end of |  |  |  | 33: 2016-02-29; 90: LOSS ←; 93: → PROFIT
|  |  | (Million Rs) |  | -40.31 | -38.92 | -37.53 | -36.14 | -34.75 | -33.36 | -31.97 | -30.58 | -29.19 | -27.8 | -26.41 | -25.02 | -23.63 | -22.24 | -20.85 | -19.46 | -18.07 | -16.68 | -15.29 | -13.9 | -12.51 | -11.12 | -9.73 | -8.34 | -6.95 | -5.56 | -4.17 | -2.78 | -1.39 | -1e-07 | 1.39 | 2.78 | 4.17 | 5.56 | 6.95 | 8.34 | 9.73 | 11.12 | 12.51 | 13.9 | 15.29 | 16.68 | 18.07 | 19.46 | 20.85 | 22.24 | 23.63 | 25.02 | 26.41 | 27.8 | 29.19 | 30.58 | 31.97 | 33.36 | 34.75 | 36.14 | 37.53 | 38.92 | 40.31 | 41.7 | 43.09 | 44.48 | 45.87 | 47.26 | 48.65 | 50.04 | 51.43 | 52.82 | 1.39 | = scale adjustment
|  |  |  | Forecasted Gross Loss/Profit at Completion: | 159: 36.1249
F | Current Cumulative Forecasted Gross Loss (-) / Profit (+) | [71 empty] | ▼ | today's value | limit at completion | bar: 168
|  |  | -2.9634 | [69 empty] | v | -2.9634 | 36.1249 | . | bar: 84 to 204
| Current Cumulative ACTUAL Gross Loss (-) / Profit (+) |  | -33.8635 | [69 empty] | a | -33.8635 | -14.5892 | . | bar: 3 to 204
A | [72 empty] | ▲ | bar: 60
|  |  |  | Realistic Gross Loss/Profit at Completion: | 51: -14.5892
5A - COMPANY CLAIMS
|  |  | (Million Rs) |  | 0.21 | 0.42 | 0.63 | 0.84 | 1.05 | 1.26 | 1.47 | 1.68 | 1.89 | 2.1 | 2.31 | 2.52 | 2.73 | 2.94 | 3.15 | 3.36 | 3.57 | 3.78 | 3.99 | 4.2 | 4.41 | 4.62 | 4.83 | 5.04 | 5.25 | 5.46 | 5.67 | 5.88 | 6.09 | 6.3 | 6.51 | 6.72 | 6.93 | 7.14 | 7.35 | 7.56 | 7.77 | 7.98 | 8.19 | 8.4 | 8.61 | 8.82 | 9.03 | 9.24 | 9.45 | 9.66 | 9.87 | 10.08 | 10.29 | 10.5 | 10.71 | 10.92 | 11.13 | 11.34 | 11.55 | 11.76 | 11.97 | 12.18 | 12.39 | 12.6 | 12.81 | 13.02 | 13.23 | 13.44 | 13.65 | 13.86 | 14.07 | 14.28 | 0.21 | = scale adjustment
|  |  |  | Forecasted Claims at Completion: | 183: 13.5
F | Current Potential Claims (Certified + to be Substantiated) | [71 empty] | ▼ | today's value | limit at completion | bar: 192
|  |  | 7.1893 | [69 empty] | v | 7.1893 | 13.5 | . | bar: 3 to 102; 195 to 204
| Current Cumulative Certified Claims |  | 0 | [69 empty] | a | 0 | 13.5 | . | bar: 195 to 204
A | [72 empty] | ▲ | bar: 192
|  |  |  | Forecasted Claims at Completion: | 183: 13.5
5B - EMPLOYER'S CLAIMS
|  |  | (Million Rs) |  | 0.21 | 0.42 | 0.63 | 0.84 | 1.05 | 1.26 | 1.47 | 1.68 | 1.89 | 2.1 | 2.31 | 2.52 | 2.73 | 2.94 | 3.15 | 3.36 | 3.57 | 3.78 | 3.99 | 4.2 | 4.41 | 4.62 | 4.83 | 5.04 | 5.25 | 5.46 | 5.67 | 5.88 | 6.09 | 6.3 | 6.51 | 6.72 | 6.93 | 7.14 | 7.35 | 7.56 | 7.77 | 7.98 | 8.19 | 8.4 | 8.61 | 8.82 | 9.03 | 9.24 | 9.45 | 9.66 | 9.87 | 10.08 | 10.29 | 10.5 | 10.71 | 10.92 | 11.13 | 11.34 | 11.55 | 11.76 | 11.97 | 12.18 | 12.39 | 12.6 | 12.81 | 13.02 | 13.23 | 13.44 | 13.65 | 13.86 | 14.07 | 14.28 | 0.21 | = scale adjustment
|  |  |  | Forecasted Employer's Claims at Completion: | 51: 4.1785
F | Current Potential Employer's Claims (Certified + to be Substantiated) | [71 empty] | ▼ | today's value | limit at completion | bar: 60
|  |  | 4.1785 | [69 empty] | v | 4.1785 | 4.1785 | . | bar: 3 to 204
| Current Cumulative Certified Employer's Claims |  | 0 | [69 empty] | a | 0 | 4.1785 | . | bar: 63 to 204
A | [72 empty] | ▲ | bar: 60
|  |  |  | Forecasted Employer's Claims at Completion: | 51: 4.1785
6 - OTHER CONTRACTUAL MATTERS
7 - COMMENTS
PROGRAMME OF WORKS
BANKABLE REVENUES
COSTS
GROSS LOSS/PROFIT
CLAIMS
CONTRACTUAL MATTERS
PROJECT MANAGER |  |  |  |  | 45: QUANTITY SURVEYOR
NAME & SURNAME |  |  |  |  | 6: SIGNATURE; 33: DATE; 45: NAME & SURNAME; 96: SIGNATURE; 123: DATE; 135: NAME & SURNAME; 168: SIGNATURE; 195: DATE
Note on DC8: Commencement date
Note on CZ11: Reporting Date (end of)
Note on DA11: Currently Approved Date for Completion
Note on CZ12: Actual Date on the PoW (modified by Current Delay/Advancement)
Note on DA12: Realistic Date for Completion
Note on B15: The Bankable Revenue INCLUDES the CERTIFIED: * Value of Works Executed (BoQ bills) * Discount (because of Sotravic's Tender) * Variations of Prices * Variations of Works * Sotravic's and Employer's Claims * Credit/Debit for Materials Note that it EXCLUDES: * Advance Payment (Received and Reimbursed) * Retention (Hold and Released) * VAT, TDS and other taxes
Note on CZ19: Current Cumulative Forecasted Bankable Revenue
Note on DA19: Original Contract Price, VAT exc.
Note on CZ20: Current Cumulative Certified Bankable Revenue
Note on DA20: Revised Contract Price, VAT exc.
Note on H22: Including the Outstanding Retention to be Released after Completion
Note on CZ27: Current Cumulative Allowables, VAT exc.
Note on DA27: Forecasted Allowables at Completion, VAT exc.
Note on CZ28: Adjusted Current Cumulative Project Cost, VAT exc.
Note on DA28: Realistic Cost to Completion, VAT exc.
Note on CZ35: Current Cumulative Allowables, VAT exc.
Note on DA35: Forecasted Allowables at Completion, VAT exc.
Note on CZ36: Adjusted Current Cumulative Project Cost, VAT exc.
Note on DA36: Realistic Cost to Completion, VAT exc.
Note on CZ43: Current Cumulative Forecasted Gross Loss/Profit
Note on DA43: Forecasted Gross Loss/Profit at Completion
Note on CZ44: Current Cumulative Actual Gross Loss/Profit
Note on DA44: Realistic Gross Loss/Profit at Completion
Note on CZ51: Current Cumulative Forecasted Gross Loss/Profit
Note on DA51: Forecasted Gross Loss/Profit at Completion
Note on CZ52: Current Cumulative Actual Gross Loss/Profit
Note on DA52: Realistic Gross Loss/Profit at Completion
Note on CZ59: Current Potential Sotravic's Claims
Note on DA59: Forecasted Sotravic's Claims at Completion
Note on CZ60: Current Cumulative Certified Sotravic's Claims
Note on DA60: Forecasted Sotravic's Claims at Completion
Note on CZ67: Current Potential Employer's Claims
Note on DA67: Forecasted Employer's Claims at Completion
Note on CZ68: Current Cumulative Certified Employer's Claims
Note on DA68: Forecasted Employer's Claims at Completion